## Slide 1: Week 4 (5-May to 11-May) Chris Porter
Goal/Task | % Done | Hours (Act.)
Learn Libero/Softconsole | 80% | 2.5
UART | 50% | 5.5*
Research | 90% | 2.75
Leadership Training | - | 1.25
Meetings (Progress and Coordination) | - | 1
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 39 hrs) | 31.2

## Slide 2: Progress made during the week (Log) (What I did)
Reviewed Final Report from W2020 to determine design specs and create a To-Do list (more organized than what was in the Project Tasks).
Read PolarFire Tutorial.
Read Libero Troubleshooting Document.
Read PolarFire FPGA Low Voltage Differential Signaling 7:1 USER GUIDE
Read core_uart_apb.c for inspiration for lvds_uart, although the lvds_uart uses uart_apd, so we may just need to write a test file for LVDS.

## Slide 3: Difficulties encountered during the week (What I did not do and why)
.

## Slide 4: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
UART | 06/07 | 8
LCD Interface | 5/31 | 4
Libero/SoftConsole | 05/17 | 1
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 5: How can we help you achieve your goals?
Is there hardware in box of hardware from STC159 Bench 2? (except the FPGA)
Status on STC159L01.c.byui.edu

## Slide 6: Week 4 (5-May to 11-May) Jonah Boe
Goal/Task | % Done | Hours (Act.)
Finish reviewing schematic for problems and errors. | 100% | 2.4
Solder the PCB | 20% | 8.75
Leadership Training | - | 1.25
Meetings (Progress and Coordination) | - | 1
Hours on task during the week (On track ≥ 13 / wk) | 13.4
Total hours on task so far this semester (On track ≥ 39 hrs) | 40.4

## Slide 7: Progress made during the week (Log) (What I did)
Soldiered all components requiring reflow oven:
Used soldier masking to prevent bridging under FPGA connector
Set up reflow profile for soldier paste
Did multiple test runs
Ran profile and tested connections
Ran new profile at higher temp and at longer duration
Soldiered all components requiring hot air gun:
Did two tests to capture profile
Reviewed schematics for tolerances
Executed

## Slide 8: Difficulties encountered during the week (What I did not do and why)
NA (on track for goals)

## Slide 9: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finish soldiering PCB | May 18, 2020 | 8
Start looking into RISC-V TMR | June 14, 2020 | 1
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13.5

## Slide 10: How can we help you achieve your goals?
So far so good

## Slide 11: Week 4 (5-May to 11-May) Spencer Cheney
Goal/Task | % Done | Hours (Act.)
Review UART, I2C, and SPI Communication | 100% | 3
Learn about register bus protocols | 90% | 3
Review Softconsole Code | 100% | 4
Hours on task during the week (On track ≥ 13 / wk) | 10
Total hours on task so far this semester (On track ≥ 39 hrs) | 32.5

## Slide 12: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
I have review the Softconsole code and now I understand what still needs to be done on Softconsole.
I learn how to implement the register bus protocols that they got set up to set the speed of various RISC-V configurations
I review how to implement UART communication

## Slide 13: Difficulties encountered during the week (What I did not do and why)
Not having admin access

## Slide 14: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Start working on SoftConsole Tests | June 7 | 6
Work through Libero section of project | May 18 | 4
Go over previous documentation and schematics | May 19 | 3
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 15: How can we help you achieve your goals?
.

## Slide 16: Week 4 (5-May to 11-May) Kyle Tolliver
Goal/Task | % Done | Hours (Act.)
Coursework – Including WIGS, Leadership, Class time, VPN, and Peer Review | 100 | 7.5
Learn Microsemi – Libero, Softconsole and VHDL | 40 | 3.5
COM Test | 15 | 2
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 39 hrs) | 36

## Slide 17: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
Learned Microsemi tools
Researched the communication tools
Looked into the code for I2C and SPI

## Slide 18: Difficulties encountered during the week (What I did not do and why)
VPN isn't letting me login

## Slide 19: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Course Work | 5/19 | 7.5
COM Test - Arduino | 5/26 | 3.5
Learn Microsemi – Libero/Softconsole | 5/26 | 2
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 20: How can we help you achieve your goals?
Tips to Libero/Softconsole
Ideas to Fix VPN login problem